## Results Framework
Result Level | Result Code | Results Statement | Indicator | Indicator Definition / Calculation | Baseline | Baseline Year | Target 2030 | Data Source | Data Collection Method | Frequency | Responsible | Disaggregation | Assumptions / Risks | Notes
Impact | IMP-01 | Improved beneficiary economic well-being | Average annual beneficiary income (₦/year) | Total annual income across valid beneficiary observations divided by the number of valid observations. | 420000 | 2026 | 600000 | Baseline/endline household survey | Structured beneficiary survey | Annual | M&E Unit | Sex, age group, LGA, beneficiary type, value chain | Economic and market conditions remain sufficiently stable. | Missing income values will not automatically be treated as zero.
Impact | IMP-02 | Improved beneficiary economic resilience | Beneficiaries reporting improved economic resilience (%) | Number of beneficiaries meeting the defined improved-resilience criterion divided by valid assessed beneficiaries × 100. | 34% | 2026 | 65% | Household survey | Structured resilience assessment | Annual | M&E Unit | Sex, age group, LGA, beneficiary type | Beneficiaries remain exposed to manageable levels of economic and climate shocks. | Higher percentage represents better performance.
Outcome | OUT-01 | Increased agricultural productivity | Average crop productivity (t/ha) | Quantity harvested in tonnes divided by cultivated area in hectares. | 1.80 t/ha | 2026 | 2.50 t/ha | Farmer survey and production records | Beneficiary survey / record review | Annual | Agriculture Technical Team / M&E | LGA, value chain, sex, age group | Inputs, weather and production conditions remain sufficiently favourable. | Valid area and harvest observations required.
Outcome | OUT-02 | Increased adoption of recommended practices | Farmers adopting at least three recommended practices (%) | Number of assessed farmers adopting at least three defined recommended practices divided by valid assessed farmers × 100. | 32% | 2026 | 65% | Farmer survey | Structured agricultural practices module | Annual | Agriculture Technical Team / M&E | Sex, age group, LGA, value chain | Farmers have access to inputs, services and technical information. | Adoption threshold = at least 3 practices.
Outcome | OUT-03 | Improved agricultural knowledge | Trained farmers demonstrating adequate knowledge (%) | Number of assessed trained farmers scoring at least 7 out of 10 knowledge questions divided by valid assessed trained farmers × 100. | 28% | 2026 | 75% | Knowledge assessment | Structured knowledge test | Annual | M&E Unit / Training Team | Sex, age group, LGA, value chain | Training content is relevant and participants engage with learning activities. | Adequate knowledge = score ≥7/10.
Outcome | OUT-04 | Improved market participation | Farmers selling through structured markets (%) | Number of valid farmer respondents selling through defined structured market channels divided by valid farmers assessed × 100. | 26% | 2026 | 55% | Farmer survey | Market access module | Annual | Market Access Team / M&E | Sex, age group, LGA, value chain | Buyers and structured market channels remain accessible. | Structured market definition will be documented in the indicator reference sheet.
Outcome | OUT-05 | Improved buyer access | Beneficiaries reporting improved buyer access (%) | Number of beneficiaries reporting improved access to buyers divided by valid assessed beneficiaries × 100. | 31% | 2026 | 70% | Beneficiary survey | Structured market access assessment | Annual | Market Access Team / M&E | Sex, age group, LGA, beneficiary type, value chain | Market linkage activities result in meaningful buyer connections. | Self-reported outcome supported by market linkage records.
Outcome | OUT-06 | Reduced post-harvest losses | Average post-harvest loss rate (%) | Quantity lost divided by quantity harvested × 100. | 22% | 2026 | 12% | Farmer survey and production records | Production and post-harvest assessment | Annual | Agriculture Technical Team / M&E | LGA, value chain, sex, age group | Improved storage, handling and transport practices are available. | Lower value represents better performance.
Outcome | OUT-07 | Improved agricultural MSME performance | Supported MSMEs reporting increased annual revenue (%) | Number of supported MSMEs reporting increased annual revenue compared with the defined comparison period divided by valid assessed supported MSMEs × 100. | 0% | 2026 | 60% | MSME survey and business records | Business survey / record review | Annual | MSME Team / M&E | Sex, age group, LGA, business type | MSMEs remain operational and market conditions support business activity. | Baseline is 0% because project-supported MSMEs have not yet received project support.
Outcome | OUT-08 | Improved MSME profitability | Average MSME annual profit (₦/year) | Total annual profit across valid MSME observations divided by the number of valid observations. | 350000 | 2026 | 550000 | MSME survey and business records | Business survey / record review | Annual | MSME Team / M&E | LGA, sex, age group, business type | MSMEs maintain operations and access viable markets. | Profit = annual sales/revenue less annual operating costs.
Outcome | OUT-09 | Improved MSME financial management | Supported MSMEs maintaining basic financial records (%) | Number of supported MSMEs meeting the defined financial-record standard divided by valid assessed supported MSMEs × 100. | 24% | 2026 | 70% | MSME survey / record verification | Record review and business survey | Annual | MSME Team / M&E | Sex, age group, LGA, business type | MSMEs are willing and able to adopt record-keeping practices. | Record standard includes defined basic business records.
Outcome | OUT-10 | Increased participation of women | Direct beneficiaries who are women (%) | Number of unique direct beneficiaries who are women divided by total unique direct beneficiaries × 100. | 35% | 2026 | 45% | Project beneficiary database | Administrative records | Quarterly | M&E Unit | LGA, beneficiary type, value chain | Women have equitable access to project activities. | Unique beneficiaries must be counted once.
Outcome | OUT-11 | Increased participation of youth | Direct beneficiaries aged 18–35 (%) | Number of unique direct beneficiaries aged 18–35 divided by total unique direct beneficiaries × 100. | 22% | 2026 | 35% | Project beneficiary database | Administrative records | Quarterly | M&E Unit | Sex, LGA, beneficiary type, value chain | Young people can access project opportunities. | Youth definition = age 18–35.
Outcome | OUT-12 | Improved economic outcomes for women | Women beneficiaries reporting increased agricultural/business income (%) | Number of assessed women beneficiaries reporting increased agricultural/business income divided by valid assessed women beneficiaries × 100. | 30% | 2026 | 60% | Beneficiary survey | Structured income/outcome assessment | Annual | M&E Unit / Gender Focal Point | LGA, age group, beneficiary type, value chain | Women can convert project support into sustained economic activity. | Applies to women beneficiaries with valid income/outcome data.
Output | OP-01 | Farmers trained | Number of farmers trained | Number of unique farmers completing defined project training activities. | 0 | 2026 | 8000 | Training attendance records | Attendance register / digital training records | Monthly | Training Team / M&E | Sex, age group, LGA, value chain | Training activities are delivered as planned. | Unique farmer counting required.
Output | OP-02 | Farmers completing climate-smart agriculture training | Number of farmers completing CSA training | Number of unique farmers completing the defined climate-smart agriculture training package. | 0 | 2026 | 5000 | CSA training records | Attendance and completion records | Monthly | Agriculture Technical Team / M&E | Sex, age group, LGA, value chain | CSA training package is delivered as scheduled. | Unique farmer counting required.
Output | OP-03 | Demonstration plots established | Number of demonstration plots established | Number of verified demonstration plots established according to project specifications. | 0 | 2026 | 80 | Project activity records | Site verification / monitoring checklist | Quarterly | Agriculture Technical Team | LGA, value chain | Suitable sites and technical resources are available. | Plots require verification before counting.
Output | OP-04 | Market-linkage events conducted | Number of market-linkage events | Number of verified market-linkage events conducted according to project specifications. | 0 | 2026 | 40 | Event records | Event reports / attendance records | Quarterly | Market Access Team | LGA, value chain, event type | Buyers and value-chain actors participate. | Each verified event counted once.
Output | OP-05 | Farmers receiving market information | Number of farmers receiving market information | Number of unique farmers receiving defined project market information services. | 0 | 2026 | 6000 | Market information records | Digital/administrative records | Monthly | Market Access Team / M&E | Sex, age group, LGA, value chain | Market information is available and distributed through functioning channels. | Unique beneficiary counting required.
Output | OP-06 | MSMEs receiving business support | Number of MSMEs receiving business support | Number of unique agricultural MSMEs receiving defined project business development support. | 0 | 2026 | 2000 | MSME support records | Administrative records / support logs | Monthly | MSME Team / M&E | Sex, age group, LGA, business type | MSMEs participate in project support activities. | Unique MSME counting required.
Output | OP-07 | MSMEs completing financial management training | Number of MSMEs completing financial management training | Number of unique MSMEs completing the defined financial management training package. | 0 | 2026 | 1500 | Training records | Attendance and completion records | Monthly | MSME Team / M&E | Sex, age group, LGA, business type | Training is delivered and MSMEs complete the required sessions. | Unique MSME counting required.
Output | OP-08 | Timely M&E implementation | Scheduled M&E activities completed on time (%) | Number of scheduled M&E activities completed by their approved deadline divided by total scheduled M&E activities × 100. | 0% | 2026 | ≥90% | M&E workplan | M&E activity tracker | Monthly | M&E Manager | Activity type, reporting period | Field and operational resources are available on schedule. | Higher percentage represents better performance.
Output | OP-09 | Timely reporting | Required reports submitted on time (%) | Number of required reports submitted by the approved deadline divided by total required reports × 100. | 0% | 2026 | 100% | Project reporting tracker | Report submission tracker | Monthly | M&E Manager / Project Management | Report type, reporting period | Reporting inputs are received on time. | Higher percentage represents better performance.
Output | OP-10 | Data quality assurance | Sampled records passing DQA (%) | Number of sampled records meeting the defined DQA pass criteria divided by total sampled records × 100. | 0% | 2026 | ≥95% | DQA records | Data Quality Assessment | Quarterly | M&E Manager | LGA, data source, indicator | Data collection and reporting systems maintain adequate quality. | DQA assesses accuracy, completeness, consistency, timeliness and integrity.

## Framework Metadata
Field | Value
Project | Agricultural Livelihoods and MSME Development Project (ALMDP)
Status | Synthetic/Simulated Portfolio Project
Geographic Focus | Kaduna State, Nigeria
Implementation Period | January 2027 – December 2030
Target Beneficiaries | 10,000
Farmers | 8,000
Agricultural MSMEs | 2,000
Number of Indicators | 24
Impact Indicators | 2
Outcome Indicators | 12
Output Indicators | 10
Baseline Year | 2026
Target Year | 2030

## Results Summary
Result Level | Number of Indicators
Impact | 2
Outcome | 12
Output | 10
Total | 24